# MAIIC_After_Build_Report_2026-10-08

# MAIIC EIR and IFRS 9 system: after-build report, 8 October 2026

What this is. On 8 October 2026 the build set out in MAIIC EIR Engine Specification v4 (7 October 2026) was carried out against the specification, section by section, on the MAICC-IFRS9 repository (branch eir_revenue_recognition, commits 32e7d99 to 09ac5da). This report says what was built, what the system proved when it ran, what the build found in the data and in the system that the specification did not know, and what is still owed. It is the comparison the specification asked for in its own section 8 (the build plan): the original specification stands as written; this report is read beside it.

The production database maiic_ifrs9 was not opened. The build was proven twice: on the demo copy (maiic_ifrs9_demo, which also holds the data of the 8 October demo), and on a throwaway database (maiic_ifrs9_bootstrap) wiped and rebuilt from nothing by the bootstrap command, which is the test the specification set for the data foundation.

## 1. In plain language

The specification said the system should load itself from E-Banker's own tables through one door with gates, build the monthly loan book from the ledger, hold the take-on schedules as data, run its engines in order, and prove the result against golden numbers, all from one command on a clean database. That is now what happens: php artisan eir:bootstrap --fresh --with-client-inputs --build --run-engines --verify takes a wiped database to a proven state in about 80 seconds, and every golden check passes. The ledger-derived loan book reproduces E-Banker's own carrying amount to the cent on 2,361 of 2,361 account-months. The interest posted from January 2025 to July 2026 is the 5,293,988,207.06 the audit found. The loan GLs at 31 December 2025 tie to the trial balance to the cent, with the two FInES GLs off by exactly the keyed-opening exception Finance has been asked to correct.

The screens moved to the suite layout with light and dark mode, and three screens the specification asked for exist: the E-Banker Feed, the Take-on Schedules and the EIR as at a Date. The transmission methods for the forward-looking adjustment are built as governed choices, each explained in the system with its preconditions checked against MAIIC's data.

Three things the specification did not know were found. The application already holds a November 2025 Mega Farm loan book of 3,490 loans across six GLs (K54.85 billion), loaded on 21 January 2026 with no ECL computed; it bears directly on the Mega Farm questions of specification section 16. The production database carries three columns no migration created, which a clean install would have lacked; a guarded migration now adds them. And the take-on schedules, compared with E-Banker's opening postings, differ on 72 of 73 mapped accounts, because they are contractual, not actual; the build keeps every take-on loan at its take-on balance, as the governed basis says, until the fees arrive.

What remains is set out in section 6: the forward-looking regression chain and the scenario-set engine (the specification's FL-1 to FL-4 and SC-1 to SC-4), the audit workbooks (CA-1 to CA-4), the Mega Farm module (section 16), the page-by-page dark-mode sweep, and the decisions MAIIC owes.

## 2. What was built, against the specification

| Spec section | What the specification asked for | Built | Where |
| --- | --- | --- | --- |
| 4.2 Governance Centre | Every open choice as a governed setting with a seeded default | Yes: 48 settings | GovernanceService::catalogue(), GovernanceServiceTest |
| 3.6 / D31 Staging | The directive's thresholds by tenor class; DPD from the oldest overdue instalment; the missed-instalment trigger | Yes | StagingThresholdSeeder, StagingService, eir:stage |
| 6.3 Landing zone | Raw tables mirroring E-Banker, append-only, versioned, every row carrying its pack | Yes, as one physical table with the query id as the logical table | migration create_ebanker_landing_zone, PackLandingService |
| 6.4 Gates | Hashes, counts, dates, register, keys; a failure names the file and row; quarantine | Yes, with key uniqueness and composite keys added | PackLandingService, 10 tests |
| 6.5 Routes | Five routes, the one in force governed | Route 1 built (command and screen upload); routes 2 to 5 are the same door with a different carrier and are not yet wired | eir:land-pack, EirFeedController::land |
| 6.2 / 6.6 Build | Methods A, B and C; maker-checker; differences first; locked periods never restated; ECL columns untouched | Yes | LoanBookBuildService, eir:build-loan-books, eir:lock-period, 11 tests |
| 6.7 History | Built on a copy by A then B and compared | Yes: B equals the stored report to the cent on every account-month but one (1 cent) | the bootstrap's verify |
| 6.8 Feed screen | Queries, loads, watermarks, quarantine, build with approval | Yes | EirFeedController, Pages/Eir/Feed/Index.vue |
| 6.9 Take-on | Landed not typed; blocks and lines with cells; gates; the build under takeon_history_basis; the screen with confirm and fees | Yes | TakeonLandingService, eir:land-takeon, EirTakeonController, 3 tests |
| 6.10 Bootstrap | One command: fresh, seed, land, build, engines, verify | Yes | eir:bootstrap |
| 6.10.1 Engine chain | Twelve engines in dependency order | Steps 1 (macro), 2 (scenario set), 3 (staging), 4 (PD transition matrix), 5 (LGD cohort workout), 6 (forward-looking chain), 7 (ECL), 8 and 9 (EIR), 10 (reconciliation) run; 11 (stress) and 12 (reports and workbooks) remain the screens' | Bootstrap::stepEngines, PdEngineService, LgdEngineService |
| 6.10.2 Golden numbers | The section 9 baselines and the year-end ties | Nine checks, all PASS | Bootstrap::stepVerify |
| 6.11 As at any date | The EIR computation for a loan or the book at any date; refused after the last posting | Yes | EirAsAtService, eir:as-at, EirAsAtController, 4 tests |
| 7.1 Ledger importer | The ledger as the primary record: interest posted and cash movements from it | Yes: interest per account-month (retiring Extract C) and the cash movements as actual transactions (retiring Extract B) | ContractInputsBuildService |
| 7.2 to 7.4 | Rate history, contract master, fees from E-Banker's tables | Yes, through the importers that already exist | ContractInputsBuildService |
| 11 Suite layout | Six groups with accents, rail, top bar, page header with breadcrumb, light and dark | Shell, shared styles and the tree built; the page-by-page dark sweep (11.9) remains | config/menu.php, AppLayout.vue, useTheme.js, NavigationTest |
| 13 Macro statistics | Codes on the series, World Bank fetcher, batches with provenance, the command with a snapshot | MS-1 to MS-3 built; the IMF WEO parser, the RBM file tab and the five-tab screen remain | MacroSeriesSeeder, WorldBankFetcherService, MacroImportService, macro:import-worldbank |
| 14.7 Transmission methods | Governed methods, each explained with live preconditions and a worked example | Yes | TransmissionMethodCatalogue, fli:method-cards, 4 tests |
| 14.3 to 14.6 Forward-looking chain | Guardrail, structural events, proxy deriver, profiler, correlation finder, regression | Yes: the suite's engines ported as they are over a bridge from MAIIC's tables; fli:correlate | FliBridgeService, app/Services/Fli/*, 1 test |
| 15 Scenario sets | The governed set: rules, shocks on the base, approval, lock, versions, back-test, sensitivity; the first set of 15.8 | Yes | ScenarioSetService, scenario:sets, Governance Centre / Scenario Sets, 3 tests |
| 12 Audit workbooks | The engine with the two columns and the Baselines sheet; the five modules | Engine ported (CA-1); IFRS 9 EIR and impairment modules drafted and built in three formats (CA-2, part of CA-4); the register, trace and pack (CA-3) and three modules remain | tools/compliance/, docs/compliance/ |
| 16 Mega Farm | The programme in the ECL module under D30 | Not started; the November 2025 book found (section 4) | section 6 |

## 3. What the system proved when it ran

The bootstrap on the wiped database, 8 October 2026 evening, then the engine chain as completed in the second round (about 90 seconds in all):

| Step | Result |
| --- | --- |
| Land the pack | 54 files, 86,000 rows, every gate passed; the five accepted exceptions recorded on the load |
| Land the take-on workbook | 100 blocks, 3,741 lines; 96 mapped, 3 not matched, 1 refused (blocks 34 and 55 both claim account 000104450000036); 64 block principals equal the take-on posting exactly; 96 blocks without a fee row, flagged, never assumed fee-free |
| Build the loan books | 26 periods, July 2024 to August 2026, by method B: 2,749 rows, 21 flagged (one account one cent off the stored report in every reported month) |
| Take-on population | 78 accounts E-Banker migrated; all 78 start at the take-on balance because no fees have been supplied |
| Contract master | 144 created, 35 held (closed before the stored report begins) |
| PLR series, fees, interest, cash | 48 PLR rows with 26 changes; 87 fee lines (arrangement 206.3 m, legal 136.7 m, other 9.5 m); 2,182 account-months of interest posted; the cash movements as actual transactions |
| Schedules and EIR | 31 schedules generated and approved under the bootstrap label; 31 EIRs solved; 12 locked; 19 blocked at the fee gate because the rulebook is unapproved |
| Revenue | 138 roll-forward rows, 12 contracts, January 2025 to August 2026; 107 months take their cash from the ledger |
| Staging | 26 periods; 1,267 / 454 / 1,028 row-months in Stages 1, 2, 3 |
| ECL | August 2026 computed on the pre-FLI PD |
| PD | Transition matrix over August 2025 to August 2026 (108 transitions): PD to Stage 3 of 35.9% from Stage 1 and 35.2% from Stage 2 |
| LGD | Cohort of 41 Stage 3 loans (4.12bn) followed twelve months: cure 21.2%, recovery 23.5%, LGD 60.25% |
| ECL, August 2026 | 8.33bn on 23.32bn gross: Stage 1 1.58bn, Stage 2 1.82bn, Stage 3 4.93bn |
| Scenario set | The first set of 15.8 approved under the bootstrap label; sensitivity on 135 loans: base 9.63bn, upside 9.00bn, downside 11.10bn, severe 12.99bn, weighted 10.24bn |
| Forward-looking chain | 1,045 driver x proxy x lag evaluations; 209 suggestions (55 recommended); 209 fits, 39 applied by the guardrail, 170 declined with reasons |
| Verify | 9 checks, 0 FAIL (the table in section 3.1) |

### 3.1 The golden numbers

| Check | Expected | Actual | Result |
| --- | --- | --- | --- |
| Interest posted Jan 2025 to Jul 2026 (ledger, types 303 and 120) | 5,293,988,207.06 | 5,293,988,207.06 | PASS |
| Derived carrying amount against the stored report (over 2 cents) | 0 differences | 0 of 2,361 account-months | PASS |
| Year-end interest batch contra on 4215 | 32,956,675.55 | 32,956,675.55 | PASS |
| Year-end interest batch contra on 4216 | −21,733,262.70 | −21,733,262.70 | PASS |
| Loan book 1050101 at 31 Dec 2025 against the trial balance | 1,368,737,810.68 | 1,368,737,810.68 | PASS |
| Loan book 1050102 | 6,434,045,052.56 | 6,434,045,052.56 | PASS |
| Loan book 1050201 (accepted exception, spec 3.5: −400,000.00) | 1,402,393,139.46 | 1,401,993,139.46 | PASS |
| Loan book 1050202 (accepted exception, spec 3.5: +1,000,000.00) | 3,808,288,656.15 | 3,809,288,656.15 | PASS |
| Loan book 1050401 | 1,827,148,120.69 | 1,827,148,120.69 | PASS |

The ECL at 31 December 2025 and 2024 against the audited allowance, and the revenue shift, are not yet golden numbers: the first needs the Mega Farm book and the approved PD route; the last is born on the first run Dr Thom approves (spec 6.10.2).

### 3.2 Staging under the directive, December 2025

Under the governed rule (Stage 2 from 31 days; Stage 3 from 91 days for a facility of 12 months or less and from 181 days otherwise; four consecutive missed instalments) the December 2025 book of 123 accounts stages 57 / 17 / 49. The November 2025 ECL model, on the uniform 181-day rule, staged its 100 loans with fewer in Stage 3. The difference is the directive's short-term rule and the missed-instalment trigger; both are governed and can be set back for comparison.

## 4. What the build found

The November 2025 Mega Farm loan book. The demo copy of the production database holds, for reporting period 2025-11, 3,490 loans across the Mega Farm GLs: 1050301 fertiliser (1,523 loans, K38.91 bn), 1050302 seed (1,180, K8.61 bn), 1050303 working capital (102, K0.90 bn), 1050304 equipment (130, K2.07 bn), 1050305 irrigation (3, K2.16 bn), 1050307 pesticides (552, K2.20 bn): K54.85 bn in all, loaded on 21 January 2026 at a uniform 15 percent rate with the arrears buckets filled and no ECL computed. Under the MEGA_FARM staging class (91 days) they stage 3,161 / 18 / 436. This is the monthly Mega Farm loan book the email to Dr Thom asks for, at least for one month; it answers part of specification section 16.8 (the book exists in the system) and sharpens the question of how the K39.76 bn provision was arrived at, since the book as loaded is mostly Stage 1 by days past due.

Schema drift. A clean migrate lacked loan_books.ead, off_balance_sheet_exposure and customer_name_imported, which the production database carries and the ECL service and reports read. They were added by hand at some point. Migration 2026_10_08_300000 adds them, guarded, so both a clean install and the production copy end in the same shape. The production copy also carries eleven working tables (legacy_loanbook, stageing_*, ebanker_loan_books, ecl_models, industry_types_updated, single_records) that no migration knows; they are left alone and listed here.

Old test rows. The production copy held 213 loan-book rows with serial contract ids (1, 2, 3 …) and sample balances in July 2024 to March 2025, from an early test import. The build retires them only when asked (--retire-stale), and only rows on a GL it covers or on no GL; the Mega Farm rows are kept.

The take-on population is 78, not 109. E-Banker's manual opening postings (operation date 31 July 2024: the 301 principal, the 303 opening interest, the 305 opening recovery, back-dated to each loan) exist for 78 accounts. The workbook's 109 facilities include ones closed before migration. The schedule balance at 31 July 2024 differs from the net opening principal on 72 of 73 mapped accounts, on both sides, because the schedules are contractual while the opening recovery is actual.

The revenue roll-forward reads the stage. Stage 3 interest is on the net basis, so the chain had to stage before the revenue run; the specification's order (EIR first, for discounting) still holds between EIR and ECL.

The feed's dates. E-Banker exports a timestamp column (LOS requests) with its time; the date gate now keeps the date part. One extract (security details) returns one row per security and account, so the register names a composite key and the gate checks uniqueness within the file.

## 5. Decisions and inputs MAIIC owes, found or confirmed by the build

| Who | What | Why it matters now |
| --- | --- | --- |
| Dr Thom or the reviewer of accounting rules | Approve the fee rulebook (30 rules seeded, three for E-Banker's own charge names) | 19 of 31 solvable EIRs are blocked at the fee gate until a reviewer approves the rules and the classifications |
| Tamanda | Which of blocks 34 and 55 belongs to account 000104450000036; the fees of the take-on loans in the yellow columns or on the Take-on Schedules screen | The refused block; all 78 take-on loans start at the take-on balance until fees exist |
| Finance | The keyed GL openings of 1050201 and 1050202 (section 3.5) | Two golden checks pass only as accepted exceptions |
| Dr Thom | How the November 2025 Mega Farm book (3,490 loans, K54.85 bn) relates to the K51.5 bn gross and K48.7 bn Stage 3 of the statements; the monthly Mega Farm books | Section 16; the ECL golden number at 31 December 2025 |
| Barry | September 2026 loan-book run (M09_03), the Mega Farm extracts (MF_01 to MF_08), the P2_13 re-run | The feed's first monthly pack; the Mega Farm build |

## 6. What is still owed

| Item | Spec | What it is | Size |
| --- | --- | --- | --- |
| Routes 2 to 5 of the feed | 6.5 | The scheduled export, the API push, the direct read, the vendor view: the same pack through the same door | Route 2: a script and a scheduler job; route 4 needs ICT's consent |
| Stress testing and the reports in the chain | 6.10.1 steps 11, 12 | Run from their screens today | Half a day each |
| FLI Adjustments screen and the fit approval | 14.6 | The chain's applied fits are proposals; a reviewer approves one on a screen and the route applies it per scenario | One day |
| The chain per scenario | 15.5 | The sensitivity uses the scenario multipliers; the full method runs the fitted relationship under each scenario's shocked path | One day after the fit approval |
| Macro screen, IMF WEO, RBM file | 13 | The five-tab screen, the WEO parser (the forecast years), the policy-rate file tab | One to two days |
| Audit workbooks: register, trace, pack; three modules | 12 (CA-3, rest of CA-4) | The register where MAIIC signs each row, the per-record trace, the auditor's pack; IFRS 7 / IAS 1, the RBM directive, Contract Schedule 1 | Two to three days |
| Mega Farm module | 16 | The programme in the ECL module under D30 with the three PD options | After Dr Thom's confirmation and the monthly books |
| Dark-mode sweep; help texts; the user manual's navigation chapter | 11.6, 11.9 | The pages that style elements directly; fifteen passages; screenshots | Ongoing; half a day for the texts |
| Tests for the PD and LGD services | 6.10.1 | The engines are proven by the bootstrap run; unit tests on a fixture are owed | Half a day |
| Golden numbers for the ECL and the revenue shift | 6.10.2 | Born on the first approved run | After the decisions in section 5 |

## 7. How to reproduce

` mysql -uroot -e "CREATE DATABASE maiic_ifrs9_bootstrap" php artisan --env=bootstrap eir:bootstrap --fresh --force-wipe --with-client-inputs --build --run-engines --verify php artisan --env=bootstrap eir:as-at 2025-12-31 php artisan --env=bootstrap fli:method-cards php artisan --env=bootstrap fli:correlate 2026-08 php artisan --env=bootstrap scenario:sets 2026-08 python tools/compliance/build_audit.py --all --env=bootstrap php artisan test tests/Feature/Eir tests/Feature/Ebanker tests/Feature/FLI/TransmissionMethodCatalogueTest.php tests/Feature/NavigationTest.php `

.env.bootstrap names the throwaway database and is git-ignored, like .env.demo. The test run above: 301 passed, 24 skipped. The 92 legacy medical tests and the five legacy FLI page tests fail on master before this work and are unrelated.

## 8. Files

Code: app/Services/Ebanker/{PackLandingService,LandingZoneReader,LoanBookBuildService,TakeonLandingService,ContractInputsBuildService}.php, app/Services/Eir/{StagingService,EirAsAtService}.php, app/Services/Macro/{WorldBankFetcherService,MacroImportService}.php, app/Services/Fli/TransmissionMethodCatalogue.php, app/Support/Fli/*, app/Console/Commands/{LandEbankerPack,BuildLoanBooks,LockReportingPeriod,StageLoanBooks,LandTakeonWorkbook,Bootstrap,EirAsAt,ImportWorldBankMacro,FliMethodCards}.php, app/Http/Controllers/{EirFeedController,EirTakeonController,EirAsAtController}.php, the migrations of 8 October 2026, config/menu.php, resources/js/{Layouts/AppLayout.vue,Jetstream/SidebarNav.vue,Jetstream/DropdownMenu.vue,navAccents.js,composables/useTheme.js,Pages/Eir/{Feed,Takeon,AsAt}/Index.vue}.

Inputs: docs/bootstrap/ (84 files in the manifest, including the original take-on workbook as received and the World Bank snapshot). Reference: docs/reference/ (the suite's engines and, from today, their support classes). Manuals: docs/manuals/installation/09-data-loading.md section 9.8 rewritten.